## Unit Test Plan
Test Case ID | Sprint | Test Description | Input Data | Expected Result | Actual Result | Status | Date Tested
TC_001 | 1 | Verify email processing module | "HELLO World" | "hello world" | "hello world" | Pass | 2025-12-02
TC_002 | 1 | Verify removal of email addresses and https..links | "Contact user@test.com" | "contact" | "contact" | Pass | 2025-12-02
TC_003 | 1 | Verify consistency of Data | customer_support_tickets.csv | DataFrame Shape > 0 rows | DataFrame Shape (5000, 3) | Pass | 2025-12-05
TC_004 | 1 | Verify label mapping for Complaints | Ticket Type: "Technical issue" | Category: "complaint" | Category: "complaint" | Pass | 2025-12-08
TC_005 | 2 | Train Logistic Regression Baseline | X_train TF-IDF Vectors | Accuracy > 80% | Accuracy: 84.67% | Pass | 2025-12-15
TC_006 | 2 | Train Naive Bayes Baseline | X_train TF-IDF Vectors | Accuracy > 70% | Accuracy: 72.10% | Pass | 2025-12-16
TC_007 | 2 | DistilBERT Tokenization | "Internet down" | Tensor IDs (List) | Tensor IDs (List) | Pass | 2025-12-19
TC_008 | 2 | DistilBERT Fine-tuning Execution | trainer.train() | Training completes without error | Training Completed | Pass | 2025-12-21
TC_009 | 2 | Model Prediction on New Data | "Refund needed" | Label: "request" | Label: "request" | Pass | 2025-12-22
TC_010 | 3 | Urgency Label Mapping | Priority: "Critical" | Urgency ID: 2 (High) | Urgency ID: 2 | Pass | 2025-12-27
TC_011 | 3 | Keyword Detection (Rule-Based) | "Fix this ASAP" | Return: 2 (High) | Return: 2 | Pass | 2025-12-30
TC_012 | 3 | ML Fallback (No Keywords) | "I need a refund" | ML Prediction (Medium/Low) | ML Prediction (Low) | Pass | 2026-01-02